## Slide 1
GO-TO-MARKET STRATEGY
Leaping AI
A Full 0→1 GTM Playbook for an AI Voice Agent Platform
Launch Sequencing • Channel Mix • Pricing Model • Sales Motion • 90-Day Execution Plan

## Slide 2
Executive Summary
The GTM thesis in one view
GTM Thesis: Run a sales-led motion targeting mid-market contact center operators (100–2,000 employees) via founder-led outbound. Use paid pilots to de-risk adoption, prove ROI with real call data, and convert to usage-based annual contracts within 90 days.
ICP
Mid-market contact centers with cloud infra; hiring freezes are the key trigger event
Sales Motion
Sales-led with a paid pilot model to de-risk the first deals
Primary Channel
Founder-led outbound: LinkedIn + email (ICE score: 504)
Pricing
Hybrid model: base platform fee plus usage-based per-minute rate
Target: $100K+ ARR booked and a repeatable, documented GTM playbook by Day 90

## Slide 3
Product Overview
What Leaping AI does, in plain English
AI Voice Agents for
Contact Centers
Automates up to 70% of inbound calls while maintaining 90%+ customer satisfaction
Natural, human-like conversations
Handles billing queries, order status, returns, and FAQs with conversational AI
Plugs into existing infrastructure
Integrates with Zendesk, Salesforce, and cloud telephony — no rip-and-replace
CSAT-safe automation
Maintains 90% customer satisfaction by escalating complex cases to human agents
Measurable cost reduction
Cuts cost-per-call from $8–12 down to a fraction — ROI is visible within weeks

## Slide 4
Market Opportunity
Why now — the cost pressure on contact centers is structural, not cyclical
$8–$12
Average cost per human-handled call today
70%
Of inbound calls are repetitive and automatable
90%
CSAT maintained with AI-handled calls
Buying Trigger Events — when companies become receptive
Recently raised a funding round
Hiring freeze announced
New CX / Ops leader joined
Peak season approaching
Why now: AI voice quality has crossed the threshold where CSAT no longer drops — removing the #1 historical objection to automation

## Slide 5
ICP & Buyer Personas
Who we sell to, and who decides
Ideal Customer Profile (4 Layers)
Firmographic | 100–2,000 employees, BFSI/Telecom/E-commerce, US/UK/ANZ, $10M–$500M revenue
Technographic | Already uses Zendesk/Salesforce + cloud telephony — no legacy on-prem PBX
Psychographic | Buyer is under CFO pressure to cut opex but fears CSAT drops from automation
Trigger Events | Hiring freeze, recent funding round, new CX leader, or approaching peak season
Buying Committee
VP Operations / CX
Economic Buyer — signs contract
“Cut cost-per-call by 70% without touching CSAT”
Team Lead / Contact Center Mgr
Champion — internal ally
“AI takes repetitive calls, your team handles complex ones”
CFO / Finance Lead
Blocker — approves budget
“ROI-positive within 60 days based on call volume”

## Slide 6
Sales Motion
Sales-led with a paid pilot model — the 5-stage journey from awareness to expansion
Why sales-led, not PLG: Replacing live call-center operations requires integration, trust, and a controlled rollout — not a self-serve signup. High potential ACV ($30K–$500K) justifies a human-led process.
1
Awareness
VP Ops discovers Leaping AI via outbound LinkedIn/email
Day 1
2
Discovery + Demo
AE qualifies call volume, runs live demo with ROI calculator
Week 1–2
3
Paid Pilot
30-day pilot on 10–15% of call volume — real data, low risk
Week 3–6
4
Close
Pilot results become the pitch — CFO and legal sign annual contract
Week 7–10
5
Expand
Land on one call type, expand to all queues, then cross-sell
Month 3+

## Slide 7
Channel Strategy
ICE-scored channel prioritization (Impact × Confidence × Ease, each 1–10)
Channel | Impact | Confidence | Ease | ICE Score | Priority
Outbound LinkedIn / Email | 9 | 8 | 7 | 504 | Do first
Referrals from customers | 10 | 6 | 7 | 420 | Engineer early
Industry events (CCW) | 7 | 7 | 5 | 245 | Month 2+
Partner integrations (Zendesk) | 9 | 5 | 4 | 180 | Month 3+
Paid LinkedIn Ads | 7 | 4 | 5 | 140 | After PMF
SEO / Content | 6 | 5 | 4 | 120 | Month 6+
Sequencing principle: At 0→1, do things that don’t scale. Outbound and founder-led referrals (highest ICE scores) come first — paid ads and SEO only after the pitch is proven and there are results to amplify.

## Slide 8
Pricing Model
Hybrid model: predictable base fee + usage-based scaling
Pilot
$3,000
/ 30 days
5,000 call minutes • 1 use case • weekly check-ins
Any prospect — de-risks first deal
Growth
$4,000
/mo + $0.08/min over 20K
Multi-queue deployment • dashboard • integrations
Mid-market (100–500 employees)
Scale
$12,000
/mo + $0.06/min over 75K
Unlimited queues • dedicated CSM • custom voice/brand
Enterprise (500+ employees)
Pricing Rationale
Pilot tier removes the #1 objection — risk — by capping cost and proving results with real data first
Base + usage gives predictable MRR while letting revenue grow naturally with customer volume (solves NRR)
Per-minute rate decreases at scale ($0.08→$0.06), incentivizing larger commitments
Anchored to savings, not build cost: $0.08/min vs. $0.30–0.50/min fully-loaded human agent cost

## Slide 9
Launch Sequencing
Each step depends on the one before it — skipping steps is the #1 reason 0→1 GTM fails
STEP 1
Product Readiness
Can we deliver reliably? Demo script + ROI calculator finalized
STEP 2
ICP Validation
Do we know who buys and why? Validated via 20–30 discovery conversations
STEP 3
Repeatable Channel
Can we find them repeatedly? Outbound engine running at volume
STEP 4
Consistent Close
Can we close consistently? Sales motion + pricing locked and proven
STEP 5
Scale What Works
Add channels, hire AEs, automate — only once Step 4 is repeatable
The 90-Day Phase Shift
Days 1–30 — Learn
Talk to 20–30 prospects, refine pitch and ICP
Days 31–60 — Execute
Outbound engine running, 3–5 pilots live
Days 61–90 — Systematize
Convert pilots, document the repeatable playbook

## Slide 10
90-Day Execution Plan
Milestones are outcomes, not activities — each unlocks the next phase
Days 1–30: Foundation
Wk1: Finalize demo, ROI calculator, target list of 100 accounts
Wk2: Founder-led outbound — 30 LinkedIn msgs/day to VP Ops
Wk3-4: Run discovery calls, refine pitch from objections
MILESTONE
3 signed pilots ($9K booked revenue)
Days 31–60: Find the Engine
Wk5-6: Deploy pilots, weekly check-ins, track CSAT + resolution
Wk7: Continue outbound — 5 more pilots signed
Wk8: Mid-pilot review, document what's working
MILESTONE
8 total pilots running, first pilot showing data
Days 61–90: Prove Repeatability
Wk9-10: Convert first 3 pilots to annual contracts
Wk11: Build case study from best-performing pilot
Wk12: Document full GTM playbook
MILESTONE
$100K+ ARR booked, repeatable playbook documented
Top-of-funnel never stops: outbound continues at full pace through every phase, even while pilots are being delivered

## Slide 11
Key Metrics Dashboard
What to track at each stage — each metric should predict the next stage's outcome
Stage | Metric | Why it matters | Day 90 Target
Top of Funnel | Outbound messages sent/week | Leading indicator — no pipeline without this | 150/week
 | Reply rate | Tells you if messaging resonates | >8%
Pipeline | Discovery calls booked | Conversion from outreach to interest | 15–20 total
 | Pilot conversion rate | % of discovery calls → paid pilot | >25%
Product / Delivery | Call automation rate | Core product metric — % of calls AI fully handles | 60–70%
 | CSAT score (AI-handled) | The #1 fear metric — must stay high | >85%
Revenue | Pilots → Contracts conversion | The real GTM validation metric | >40%
 | ARR booked | The ultimate scoreboard | $100K
Golden rule: If a metric doesn't predict a downstream outcome, it's vanity — don't track it.

## Slide 12
By Day 90
Success looks like this
$100K+
ARR booked from 2–3 converted pilots
8
Total pilots run, proving the pitch works
>85%
CSAT maintained on AI-handled calls
1
Documented, repeatable GTM playbook
What unlocks next
Hire the first AE
to scale outbound beyond founder-led capacity, using the documented playbook as onboarding material.
Layer in Marketing-led + Partner-led motions
— publish ROI case studies for inbound, and explore Zendesk/Genesys integration partnerships for warm pipeline.